## Master Test List
Motorola Solutions - Stability Tests and Priority
Test Number | Stability Test | Priority Number | Priority Type
1 | Make a 2G voice call from the phone book | 3 | High | 26 | High Priority
2 | Make a 3G voice call from the phone book | 3 | High | 21 | Medium Priority
3 | Make a LTE voice call from the phone book | 0 | Do not test | 23 | Low Priority
4 | Make a 2G voice call from the call history list | 3 | High | 11 | Do not test
5 | Make a 3G voice call from the call history list | 3 | High | 81 | Total Tests
6 | Make a LTE voice call from the call history list | 0 | Do not test
7 | Receive a voice call | 3 | High
8 | Delete a contact from the phone book | 2 | Medium
9 | Add a contact to the phone book | 2 | Medium
10 | Send an SMS maximum number of characters with out requiring the message to be segmented | 3 | High
11 | Send a MMS with a 1MB audio attachment or largest size supported by the device | 2 | Medium
12 | Send a MMS with a 1MB video attachment or largest size supported by the device | 2 | Medium
13 | Send a MMS with a 1MB picture attachment or largest size supported by the device | 3 | High
14 | Open a MMS with a 1MB audio attachment or largest size supported by the device | 2 | Medium
15 | Open a MMS with 1MB video or largest size supported by the device | 2 | Medium
16 | Open a MMS with a 1MB image or largest size supported by the device | 3 | High
17 | Open a SMS | 3 | High
18 | Send an email with no attachment | 3 | High
19 | Send an email with an attachment | 2 | Medium
20 | Open an email | 3 | High
21 | Add 2 buddies to the buddy list for each IM community | 0 | Do not test
22 | Send an IM to each buddy in the list for each supported IM community | 0 | Do not test
23 | Delete 2 buddies for the buddy list for each support IM community | 0 | Do not test
24 | Open the native browser and go to the AT&T home page | 1 | Low
25 | Navigate to a link and click on the link | 1 | Low
26 | Top Web Sites | 2 | Medium
27 | Start the Sesame client and load the Sesame home page | 0 | Do not test
28 | Sesame client - navigate to a link and click on the link | 0 | Do not test
29 | Open/Close the Store Front Client | 0 | Do not test
30 | Download a Java application/game | 1 | Low
31 | Storefront Application download | 0 | Do not test
32 | Close the application store front | 0 | Do not test
33 | Open a downloaded Java Game and then close a Java Game | 1 | Low
34 | Open a downloaded application from the storefront | 0 | Do not test
35 | Delete a downloaded Java game | 1 | Low
36 | Delete a downloaded Native application | 1 | Low
37 | Add an appointment to the calendar | 2 | Medium
38 | Set an alarm | 2 | Medium
39 | Delete the an appointment in the calendar | 2 | Medium
40 | Delete the an alarm | 2 | Medium
41 | Add a task | 1 | Low
42 | Open a task | 1 | Low
43 | Delete a task | 1 | Low
44 | Record a 30s video | 3 | High
45 | Play back a 30s video | 3 | High
46 | Delete a video | 2 | Medium
47 | Take a picture | 3 | High
48 | Open a picture | 3 | High
49 | Delete a picture | 2 | Medium
50 | Record a 5s audio message | 1 | Low
51 | Listen to a 5s audio message | 1 | Low
52 | Delete a audio message | 1 | Low
53 | Play video streaming content using device browser and video player | 2 | Medium
54 | Open/close the music player | 2 | Medium
55 | Open Music Player and play a music file | 2 | Medium
56 | Close the music player | 2 | Medium
57 | Open and set a theme | 1 | Low
58 | Make a phone call | 3 | High
59 | Switch from the telephony application to each running application | 3 | High
60 | End the phone call | 3 | High
61 | Start a browser session and load home page | 3 | High
62 | Switch from the browser application to each running application | 3 | High
63 | Close the browser | 3 | High
64 | Menu Nav | 2 | Medium
65 | Turn the WiFi radio off and on | 3 | High
66 | Connect/Disconnect to a WiFi network | 3 | High
67 | Turn NFC Off and On | 3 | High
68 | Data Stability Uplink - Tether | 1 | Low
69 | Data Stability Uplink – BT | 2 | Medium
70 | Data Stability Uplink – Mobile Hotspot | 3 | High
71 | Data Stability Downlink - Tether | 1 | Low
72 | Data Stability Downlink – BT | 2 | Medium
73 | Data Stability Downlink – Mobile Hotspot | 3 | High
74 | Connect the charger to the device twice in a 24 hour period | 1 | Low
75 | Disconnect the charger from the device twice in a 24 hours period | 1 | Low
76 | Connect a wired handsfree accessory to the device twice in a 24 hour period | 1 | Low
77 | Disconnect the wired handsfree accessory twice in a 24 hour period | 1 | Low
78 | Open the flip on the device twice in a 24 hours period | 1 | Low
79 | Close the flip on the device twice in a 24 hour period | 1 | Low
80 | Connect a Bluetooth accessory twice in a 24 period | 1 | Low
81 | Disconnect a Bluetooth accessory twice in a 24 period | 1 | Low

## Sortable List
Motorola Solutions - Stability Tests and Priority
Test Number | Stability Test | Priority Number | Priority Type
1 | Make a 2G voice call from the phone book | 3 | High
2 | Make a 3G voice call from the phone book | 3 | High
3 | Make a LTE voice call from the phone book | 0 | Do not test
4 | Make a 2G voice call from the call history list | 3 | High
5 | Make a 3G voice call from the call history list | 3 | High
6 | Make a LTE voice call from the call history list | 0 | Do not test
7 | Receive a voice call | 3 | High
8 | Delete a contact from the phone book | 2 | Medium
9 | Add a contact to the phone book | 2 | Medium
10 | Send an SMS maximum number of characters with out requiring the message to be segmented | 3 | High
11 | Send a MMS with a 1MB audio attachment or largest size supported by the device | 2 | Medium
12 | Send a MMS with a 1MB video attachment or largest size supported by the device | 2 | Medium
13 | Send a MMS with a 1MB picture attachment or largest size supported by the device | 3 | High
14 | Open a MMS with a 1MB audio attachment or largest size supported by the device | 2 | Medium
15 | Open a MMS with 1MB video or largest size supported by the device | 2 | Medium
16 | Open a MMS with a 1MB image or largest size supported by the device | 3 | High
17 | Open a SMS | 3 | High
18 | Send an email with no attachment | 3 | High
19 | Send an email with an attachment | 2 | Medium
20 | Open an email | 3 | High
21 | Add 2 buddies to the buddy list for each IM community | 0 | Do not test
22 | Send an IM to each buddy in the list for each supported IM community | 0 | Do not test
23 | Delete 2 buddies for the buddy list for each support IM community | 0 | Do not test
24 | Open the native browser and go to the AT&T home page | 1 | Low
25 | Navigate to a link and click on the link | 1 | Low
26 | Top Web Sites | 2 | Medium
27 | Start the Sesame client and load the Sesame home page | 0 | Do not test
28 | Sesame client - navigate to a link and click on the link | 0 | Do not test
29 | Open/Close the Store Front Client | 0 | Do not test
30 | Download a Java application/game | 1 | Low
31 | Storefront Application download | 0 | Do not test
32 | Close the application store front | 0 | Do not test
33 | Open a downloaded Java Game and then close a Java Game | 1 | Low
34 | Open a downloaded application from the storefront | 0 | Do not test
35 | Delete a downloaded Java game | 1 | Low
36 | Delete a downloaded Native application | 1 | Low
37 | Add an appointment to the calendar | 2 | Medium
38 | Set an alarm | 2 | Medium
39 | Delete the an appointment in the calendar | 2 | Medium
40 | Delete the an alarm | 2 | Medium
41 | Add a task | 1 | Low
42 | Open a task | 1 | Low
43 | Delete a task | 1 | Low
44 | Record a 30s video | 3 | High
45 | Play back a 30s video | 3 | High
46 | Delete a video | 2 | Medium
47 | Take a picture | 3 | High
48 | Open a picture | 3 | High
49 | Delete a picture | 2 | Medium
50 | Record a 5s audio message | 1 | Low
51 | Listen to a 5s audio message | 1 | Low
52 | Delete a audio message | 1 | Low
53 | Play video streaming content using device browser and video player | 2 | Medium
54 | Open/close the music player | 2 | Medium
55 | Open Music Player and play a music file | 2 | Medium
56 | Close the music player | 2 | Medium
57 | Open and set a theme | 1 | Low
58 | Make a phone call | 3 | High
59 | Switch from the telephony application to each running application | 3 | High
60 | End the phone call | 3 | High
61 | Start a browser session and load home page | 3 | High
62 | Switch from the browser application to each running application | 3 | High
63 | Close the browser | 3 | High
64 | Menu Nav | 2 | Medium
65 | Turn the WiFi radio off and on | 3 | High
66 | Connect/Disconnect to a WiFi network | 3 | High
67 | Turn NFC Off and On | 3 | High
68 | Data Stability Uplink - Tether | 1 | Low
69 | Data Stability Uplink – BT | 2 | Medium
70 | Data Stability Uplink – Mobile Hotspot | 3 | High
71 | Data Stability Downlink - Tether | 1 | Low
72 | Data Stability Downlink – BT | 2 | Medium
73 | Data Stability Downlink – Mobile Hotspot | 3 | High
74 | Connect the charger to the device twice in a 24 hour period | 1 | Low
75 | Disconnect the charger from the device twice in a 24 hours period | 1 | Low
76 | Connect a wired handsfree accessory to the device twice in a 24 hour period | 1 | Low
77 | Disconnect the wired handsfree accessory twice in a 24 hour period | 1 | Low
78 | Open the flip on the device twice in a 24 hours period | 1 | Low
79 | Close the flip on the device twice in a 24 hour period | 1 | Low
80 | Connect a Bluetooth accessory twice in a 24 period | 1 | Low
81 | Disconnect a Bluetooth accessory twice in a 24 period | 1 | Low

## Completed Items
Motorola Solutions - Stability Tests and Priority
[7 empty] | Total | Completed |  | Percent Completed
Test Number | Stability Test | Priority Number | Priority Type | Completed | Status | Notes | 26 | 12 | High Priority | 46.15%
1 | Make a 2G voice call from the phone book | 3 | High | 6-07-2013 | Complete |  | 21 | 12 | Medium Priority | 57.14%
2 | Make a 3G voice call from the phone book | 3 | High | 6-10-2013 | Complete |  | 11 | 9 | Low Priority | 81.82%
4 | Make a 2G voice call from the call history list | 3 | High | 6-10-2013 | Complete |  | 58 | 33 | Total Tests | 56.9%
5 | Make a 3G voice call from the call history list | 3 | High | 6-10-2013 | Complete
7 | Receive a voice call | 3 | High | 6-07-2013 | Complete
10 | Send an SMS maximum number of characters with out requiring the message to be segmented | 3 | High
13 | Send a MMS with a 1MB picture attachment or largest size supported by the device | 3 | High
16 | Open a MMS with a 1MB image or largest size supported by the device | 3 | High
17 | Open a SMS | 3 | High
18 | Send an email with no attachment | 3 | High
20 | Open an email | 3 | High
44 | Record a 30s video | 3 | High |  | In progress | Awaiting device bug fix from Motorola.
45 | Play back a 30s video | 3 | High |  | In progress | Awaiting device bug fix from Motorola.
47 | Take a picture | 3 | High |  | In progress | Awaiting device bug fix from Motorola.
48 | Open a picture | 3 | High |  | In progress | Awaiting device bug fix from Motorola.
58 | Make a phone call | 3 | High | 6-10-2013 | Complete
59 | Switch from the telephony application to each running application | 3 | High | 6-10-2013 | Complete
60 | End the phone call | 3 | High | 6-10-2013 | Complete
61 | Start a browser session and load home page | 3 | High | 5-22-2013 | Complete | Sets homepage to default: google.
62 | Switch from the browser application to each running application | 3 | High | 5-22-2013 | Complete | Exits browser via taskbar and enters VNC server app.
63 | Close the browser | 3 | High | 5-22-2013 | Complete | Returns to home screen, does not kill app.
65 | Turn the WiFi radio off and on | 3 | High
66 | Connect/Disconnect to a WiFi network | 3 | High
67 | Turn NFC Off and On | 3 | High | 6-05-2013 | Complete | Turns function on/off, doesn't pass data to another device.
70 | Data Stability Uplink – Mobile Hotspot | 3 | High
73 | Data Stability Downlink – Mobile Hotspot | 3 | High
8 | Delete a contact from the phone book | 2 | Medium | 5-22-2013 | Complete
9 | Add a contact to the phone book | 2 | Medium | 5-22-2013 | Complete
11 | Send a MMS with a 1MB audio attachment or largest size supported by the device | 2 | Medium
12 | Send a MMS with a 1MB video attachment or largest size supported by the device | 2 | Medium
14 | Open a MMS with a 1MB audio attachment or largest size supported by the device | 2 | Medium
15 | Open a MMS with 1MB video or largest size supported by the device | 2 | Medium
19 | Send an email with an attachment | 2 | Medium
26 | Top Web Sites | 2 | Medium | 5-22-2013 | Complete | Uses browser to visit Top 5 websites by traffic.
37 | Add an appointment to the calendar | 2 | Medium | 5-22-2013 | Complete
38 | Set an alarm | 2 | Medium | 5-21-2013 | Complete
39 | Delete the an appointment in the calendar | 2 | Medium | 5-22-2013 | Complete
40 | Delete the an alarm | 2 | Medium | 5-21-2013 | Complete
46 | Delete a video | 2 | Medium |  | In progress | Awaiting device bug fix from Motorola.
49 | Delete a picture | 2 | Medium |  | In progress | Awaiting device bug fix from Motorola.
53 | Play video streaming content using device browser and video player | 2 | Medium | 6-05-2013 | Complete
54 | Open/close the music player | 2 | Medium | 5-20-2013 | Complete
55 | Open Music Player and play a music file | 2 | Medium | 5-20-2013 | Complete | Requires set up Audio Sample 1 file.
56 | Close the music player | 2 | Medium | 5-20-2013 | Complete | Returns to home screen, does not kill app.
64 | Menu Nav | 2 | Medium | 5-30-2013 | Complete
69 | Data Stability Uplink – BT | 2 | Medium
72 | Data Stability Downlink – BT | 2 | Medium
24 | Open the native browser and go to the AT&T home page | 1 | Low | 5-23-2013 | Complete
25 | Navigate to a link and click on the link | 1 | Low | 5-30-2013 | Complete
30 | Download a Java application/game | 1 | Low | 6-05-2013 | Complete
33 | Open a downloaded Java Game and then close a Java Game | 1 | Low | 6-05-2013 | Complete
35 | Delete a downloaded Java game | 1 | Low | 6-05-2013 | Complete
36 | Delete a downloaded Native application | 1 | Low | 6-03-2013 | Do not test | Coverage obtained via test 35.
41 | Add a task | 1 | Low | 6-05-2013 | Do not test | Function not supported, confirmed by Motorola.
42 | Open a task | 1 | Low | 6-05-2013 | Do not test | Function not supported, confirmed by Motorola.
43 | Delete a task | 1 | Low | 6-05-2013 | Do not test | Function not supported, confirmed by Motorola.
50 | Record a 5s audio message | 1 | Low | 5-23-2013 | Complete
51 | Listen to a 5s audio message | 1 | Low | 5-23-2013 | Complete
52 | Delete a audio message | 1 | Low | 5-23-2013 | Complete
57 | Open and set a theme | 1 | Low | 5-30-2013 | Complete
68 | Data Stability Uplink - Tether | 1 | Low
71 | Data Stability Downlink - Tether | 1 | Low
74 | Connect the charger to the device twice in a 24 hour period | 1 | Low | 5-23-2013 | Do not test | Non-automatable.
75 | Disconnect the charger from the device twice in a 24 hours period | 1 | Low | 5-23-2013 | Do not test | Non-automatable.
76 | Connect a wired handsfree accessory to the device twice in a 24 hour period | 1 | Low | 5-23-2013 | Do not test | Non-automatable.
77 | Disconnect the wired handsfree accessory twice in a 24 hour period | 1 | Low | 5-23-2013 | Do not test | Non-automatable.
78 | Open the flip on the device twice in a 24 hours period | 1 | Low | 5-17-2013 | Do not test | Non-automatable.
79 | Close the flip on the device twice in a 24 hour period | 1 | Low | 5-17-2013 | Do not test | Non-automatable.
80 | Connect a Bluetooth accessory twice in a 24 period | 1 | Low | 5-23-2013 | Do not test | Non-automatable.
81 | Disconnect a Bluetooth accessory twice in a 24 period | 1 | Low | 5-23-2013 | Do not test | Non-automatable.
3 | Make a LTE voice call from the phone book | 0 | Do not test | 5-16-2013 | Do not test list
6 | Make a LTE voice call from the call history list | 0 | Do not test | 5-16-2013 | Do not test list
21 | Add 2 buddies to the buddy list for each IM community | 0 | Do not test | 5-16-2013 | Do not test list
22 | Send an IM to each buddy in the list for each supported IM community | 0 | Do not test | 5-16-2013 | Do not test list
23 | Delete 2 buddies for the buddy list for each support IM community | 0 | Do not test | 5-16-2013 | Do not test list
27 | Start the Sesame client and load the Sesame home page | 0 | Do not test | 5-16-2013 | Do not test list
28 | Sesame client - navigate to a link and click on the link | 0 | Do not test | 5-16-2013 | Do not test list
29 | Open/Close the Store Front Client | 0 | Do not test | 5-16-2013 | Do not test list
31 | Storefront Application download | 0 | Do not test | 5-16-2013 | Do not test list
32 | Close the application store front | 0 | Do not test | 5-16-2013 | Do not test list
34 | Open a downloaded application from the storefront | 0 | Do not test | 5-16-2013 | Do not test list